## Startup
ValueDraft Debug
# | Page | Sub-Page/Path | Description | Notes/Steps to obtain bug | Pic ref in Error.doc | Fixed | Notes | Verified (Y/N)
1 | Startup | N/A | Failed to load image | Error rec'vd upon starting | a | Y |  | Y
2 | Startup | N/A | Change website to www.valuedraft.com |  |  | Y |  | Y
3 | Startup | Create/Owners Tab | Number the Lines 1-(Total Owners) |  |  | Y |  | Y
4 | Startup | Create/Owners Tab | Tab to next entry- currently pressing tab goes to the buttons below. |  |  | Y |  | Y
6 | Create | Create/Positions | SS default should be 1 |  |  | Y |  | y
10 | Create | Create/Players | Extend the borders wider (some American league teams are close to the border) (Arizona Diamondbacks is on the border) |  |  | Y |  | y
11 | Create | Create/Scoring | In the title-Hitting Categories- "Categories" is spelled wrong |  |  | Y |  | Y
12 | Create | Create/NA | Allow user to click the tabs above to advance or go back. | I found myself wanting to use the tabs. Can we add this and create error messages when user clicks Finish and its missing data. |  | Y |  | y
13 | Create | Create/NA | I clicked save and recv'd error message | Create new league, enter Name, Next, entered owners names, Next, changed SS to 1, SP to 0, RP to 0, Next, clicked All NL Teams, Next, Clicked Save. But the league existed when I re-opened the program, but see #14. | b | Y |  | Y
14 | Create | Edit/Players tab | Clicking All NL Teams does not include Washington Nationals, but includes Toronto Blue Jays instead when editing the league | Created a league (#13), clicked All NL teams, saved the league. Edited the league and the players tab did not have the Washington Nationals checked, but had Toronto Blue Jays checked (last entries for both AL and NL) |  | Y |  | Y
15 | Create | Edit/NA | I edited a league I created (see#14 I edited this error) and clicked Save and received an error | Steps: Edit League, next, next, next, click Washington National, uncheck Toronto Blue Jays, next, Save | c | Y |  | Y
17 | Create | Create/Positions | Default should be SP-0, RP- 0 and P-9 |  |  | Y |  | Y
1 | Create | N/A | The Icon in the taskbar is fuzzy when running the program. |  | a |  | Let's fix later.
2 | Create | Owners | Provide a warning message when the user types the same exact owner name as a previous owner. Message should read: Warning. Owner already exists. | Only option to close the window is "OK". This will warn the user that they have entered the same owner name which could cause confusion when drafting. The program should allow the same owner name as long as it does not confuse the two owners when drafting.
3
18
19
20
21
22
23
24

## Main
ValueDraft Debug
# | Page | Sub-Page/Path | Description | Notes/Steps to obtain bug | Pic ref in Error.doc | Fixed | Notes | Verified (Y/N)
1 | Startup | N/A | Failed to load image | Error rec'vd upon starting | a | Y |  | Y
2 | Startup | N/A | Change website to www.valuedraft.com |  |  | Y |  | Y
3 | Startup | Create/Owners Tab | Number the Lines 1-(Total Owners) |  |  | Y |  | Y
4 | Startup | Create/Owners Tab | Tab to next entry- currently pressing tab goes to the buttons below. |  |  | Y |  | Y
6 | Startup | Create/Positions | SS default should be 1 |  |  | Y |  | y
10 | Startup | Create/Players | Extend the borders wider (some American league teams are close to the border) (Arizona Diamondbacks is on the border) |  |  | Y |  | y
11 | Startup | Create/Scoring | In the title-Hitting Categories- "Categories" is spelled wrong |  |  | Y |  | Y
12 | Startup | Create/NA | Allow user to click the tabs above to advance or go back. | I found myself wanting to use the tabs. Can we add this and create error messages when user clicks Finish and its missing data. |  | Y |  | y
13 | Startup | Create/NA | I clicked save and recv'd error message | Create new league, enter Name, Next, entered owners names, Next, changed SS to 1, SP to 0, RP to 0, Next, clicked All NL Teams, Next, Clicked Save. But the league existed when I re-opened the program, but see #14. | b | Y |  | Y
14 | Startup | Edit/Players tab | Clicking All NL Teams does not include Washington Nationals, but includes Toronto Blue Jays instead when editing the league | Created a league (#13), clicked All NL teams, saved the league. Edited the league and the players tab did not have the Washington Nationals checked, but had Toronto Blue Jays checked (last entries for both AL and NL) |  | Y |  | Y
15 | Startup | Edit/NA | I edited a league I created (see#14 I edited this error) and clicked Save and received an error | Steps: Edit League, next, next, next, click Washington National, uncheck Toronto Blue Jays, next, Save | c | Y |  | Y
17 | Startup | Create/Positions | Default should be SP-0, RP- 0 and P-9 |  |  | Y |  | Y
1 | N/A | N/A | Icon on taskbar not clear. | Can I provide a different sized icon file so the icon on the taskbar when running the program is crystal clear (not fuzzy)? | a | Y
4 | Main | Players | Change Icon in upper left to the baseball image |  |  | Y
10 | Main | Players | Edit Columns filter button does not reset. | Click Edit Columns. Select SLG. Select Edit Columns again. Un-Select SLG. Select Edit columns again. SLG is still checked. |  | Y
11 | Main | Players | Allow user to click and drag columns to move location.
12 | Main | Players | Allow user to sort by clicking on column title | A second click on the same column should sort the other way- example click HR, sorts largest to smallest, click HR again, should sort smallest to largest. Error received when clicking CurrValue and BegValue. Also, Can it be faster? seems to be a delay after clicking. |  | Y | All works except I cannot sort by BegValue and clicking # twice does not sort largest to smallest. - Fixed | Y
14 | Main | Players | Make the Notes column 4 times wider than it is now as default. | Adjust the width of a column. Sort by any column. All columns revert to original width. |  | Y | Once you sort by any column, it reverts to original size - Fixed
15 | Main | Players | Move the buttons closer together. This is for all the buttons at the top. The draft section (Player, Owner, AmtPaid, Position, Draft)- move them closer together so they are spaced evenly apart but not so much space as there is now. Example for size of space- place a little more space than the space between MI and All Hitters Then same for the next row (Players, Rosters, Projected Standings, Draft Results- these should have some space between them, but make them much tighter and also the next row- the position filters are good for hitters, but shorten the space between the Hitter Filters and the Pitcher filters. Then same for the final row, shorten the space between all the buttons. |  |  | NB | This is not a bug. When there is a different theme or different font selected or different screen resolution or different OS those calculations will be different.
18 | Main | Players | Allow user to right click on a new player and present the right click menu. | With Row 6 highlighted, right click on row 20. User should be presented the right click menu option for row 20. |  | Y
23 | Main | Players | Change the width of the dialog boxes and buttons. | Starting at the top- The two Owner drop downs should be wider. Amt Paid narrower. Position narrower. All Players button narrower. Top button narrower. |  | NB | See the explanation of #15
24A | Main | Players | When searching for a player, sometimes the player will be highlighted but not visible on the screen. The user should type in the search, select the player and the player should be visible and highlighted with a few players (about 10) visible above him. | Type Mat in the search field and select Mat Latos. You have to scroll to be able to see his row. |  | Y | Do the same thing. Mat Latos appears, but then type "Ryan" and select Ryan Braun, you have to scroll up to find him. / Fixed. Please verify
26 | Main | Players | Strange behavior occurs in the Player search field with certain characters. | Type Mc- it changes to ":" |  | Y
27 | Main | Players | Can we add another Edit Columns button to the right of the Notes column in the draft section. Similar to the edit columns button below, this will allow the user to edit the columns visible for the player in the draft section. Would we need two? Edit Hitters Columns and Edit Pitchers Columns? ideally one button could do it. |  |  |  | It is currently in the row below the column titles (where the stats would be shown). Can you move it to the row with the column titles and make it a button like the others (not encompassing the row/column) (e.g. like the Draft button.
35 | Main | N/A | When making changes to the Demo leagues, save the changes so on startup the changes will be present. | Open program, select Matt Kemp and draft to Team 1. Select League (menu) Save and exit. Error received and program does not close. See pic. | b. | Y | see Elance note / Fixed
36 | Main | N/A | On the toolbar, change File to "League". |  |  | Y
37 | Main | N/A | When selecting a demo league. Allow the user to reset the league to its default. Place this in the League (old name- File) Menu. Call it "Reset to Default". Then provide a warning message: "This will reset the league to default values and unassign all players. Do you want to reset?" provide two buttons- Yes and Cancel | Under the Edit menu, there is a "Clear all drafted players" option. Let's move this to the "League" menu. |  | Partial - menu is in place, but the code handlers are not | So the League menu will have "Reset to Default" and "Clear All Drafted Players". Reset- will clear the players and reset all columns and values and stats to original. Clear option will just unassign all the players. (all values and stats and columns that were edited will remain.)
38 | Main | Players | Drafting a pitcher returns an error: Position is already taken. Please select another position. | Right click Roy Halladay, select Draft Player. Select an owner, click Draft. Returns the confirm screen, then the error. |  | Y | Seems to do this for all pitchers.
39 | Main | Players | All Hitters and All Pitchers filters don’t work | Selecting All Hitters should only show all players that are NOT position SP, RP, P. Selecting All Pitchers should show only all players at position SP, RP, P. |  | Y
40 | Main | Players | Add "All Players" Button between All Hitters and P | This "filter" resets/unselects all position filters. It will show all players adhering to the rules in the "Players Filter" section. Example: user has C and 1B selected and also has Show Drafted Players slected- this would show all drafted players at position C and 1B. The user then selects "All Players". This would show All Players that have been drafted. Its a quick way to turn off the position filter. |  | Y | Select All Hitters, then select All Players- it does not bring the pitchers back. - Fixed. Please verify- It now does not bring the hitters back, shows only Pitchers. This still does not work. Clicking All Players does not bring the pitchers back. / FIXED
43 | Main | Players | The position filters are not working. CI should show all players eligible at 1B and 3B, MI should show all SS and 2B. | Click CI, all 1B and 3B are shown. Click MI, it goes blank. 5/20- It works initially, but then loses the filter. Click C, it shows all catchers, click 1B, it shows all 1B, but then click 2B, the filter is wrong, then click C again and that is wrong as well. 5/20- Strange. Now when I clicked All Players and go back to the filters it works again. So something strange is happening. Also- MI- that should show players at 2B OR SS, it looks like it is showing 2B AND SS. Same with CI except its 1B OR 3B not 1B AND 3B. |  | Y | Notes in bolld is fixed. Please verify
45 | Main | Players | The Demo Roto league has incorrect Saves data for Myers and Lopez.
46 | Main | Players | In the draft section, upon opening the program, place player #1 (or highest ranked) in the draft section, displaying their stats. | Example, in the demo league, matt kemp would be displayed and his stats. |  | Y
47 | Main | Players | User should be able to double click into the Notes cell and free form type notes. A single click of the notes cell should highlight the row for that player. |  |  | Y |  | Y
48 | Main | Roster section on left | Format stats using the same format as the main players page. E.g. AVG= .XXX HR= X or XX, Runs= X, XX, or XXX (no decimals) |  |  | Y
49 | Main | Players | When the position filter is selected, it is not possible to select a row (player) |  |  | Y
50 | Main | Draft Player | When the player is selected for draft and he has multiple eligible positions only first position is available for selection as drafted position. |  |  | Y | When a player with multiple eligible positions is selected in the draft section, the first position should show, but the drop down should include all eligible positions.
51 | Main | Roster section on left | Expand the hitter and pitcher sections so all positions are available. |  |  |  | see picture file "Capture" on elance
52 | Main | Roster section on left | Can we update the Roster real time without a refresh? | Draft Tulowitzki to Owner "Team 1". On the roster section on left, select Team 1. Tulowitzki is visible. Now Draft Clayton Kershaw to Team 1. he does not show unless you click on another owner and then click back to Team 1. |  | Y | Kershaws stats show in the Pitcher totals on roster section, but his name does not populate under "P". If I click to Team2 then back to Team1, Kershaw's name is there. | N
53 | Main | Roster section on left | Change format of Avg$/player Left to $XX.XX and round to nearest $.10 |  |  | Y |  | Y
54 | Main | Draft Player | The eligible positions displayed are incorrect as you draft players. The drop down remembers other positions of other players drafted. | Open program, right click and draft Joey Votto to Team1. His eligible position is 1B, but it shows 1B and OF (because Matt Kemp was there). Now right click and draft Roy Halladay, he is eligible at SP, but it shows 1B and OF as well. |  | Y |  | y
55 | Main | Draft Player | Eligible Positions- In the drop down in the draft section, all hitters should show them eligible at U (last option on drop down). 2B and SS should show MI (2nd to last option) 1B and 3B should show CI (2nd to last). | Example: Troy Tulowitzki position drop down in the draft section should be SS, MI, U. |  | Y | Almost. Just add MI to the 2B and SS and add CI to the 1B and 3B
56 | Main | Both: players and draft player | Name completer should honor player status: available or drafted | 5/20- Still seems to be off a bit. I followed the steps in Notes and when I typed R, it only showed Ryan Theriot, but it should have shown all players that start with R (example- Ryan Braun was missing. Then when I clicked off, I could not get the search to work again. Type in any letter, it did not bring up any players. - Ficed. Please verify |  | Y | Open Demo, Draft Matt Kemp to Team1. Then select the filter: Show Available Players. Then type "ry" in the search…it shows nothing, but should display: all players named Ryan. And in the event one of the Ryans was drafted, that Ryan should not be shown because the user has selected the filter: Show Available Players.
57 | Main | Both: players and draft player | Name completer should honor player position | A) Draft section- Only use the "available" filter to display players in the name completer. If the user is filtered by SS in the players section and they search for a player to be drafted in the draft section that is an OF, the name completer should show the name (as long as the player is available to be drafted) - Yes, in the draft section player position shouldn't be honored. Only Available/Drafted status B) Player Section- the name completer should only show players that appear with the filters. 5/20- Since this is related to #56- I will leave this for now. |  | Y | Open Demo, Draft Matt Kemp to Team1. Then select the filer: Show Available Players. Then select filer: SS. Re: A)Then type "ry" in the Player field in the draft section…it shows nothing, but should display: all players named Ryan. Re: B) Now type J in the Search field for players. It should only show the SS that have not been drafted (because the filter: Show Available Players has been selected)and that begin with J, but it shows all players that begin with J.
58 | main | Search | Clayton Kershaw seems to be missing from the name completer | Open program, draft Ryan Braun to Team 2. Then type "cl" in the players search, only clint barmes shows, not clayton kershaw |  | Y | 5/20- This is related somewhat to 56 and 57 so I will test this when we get that fixed.
59 | Main | Players | Sorting by HRs does not work on the double click. | Click HR to sort by HR largest to smallest. It works. Click again and the numbers/stats stay but the names change. |  | Y
60 | Main | N/A | make the default Owner, the first team in the list for the roster drop down section. | In the Demo, at startup, Team1 should be selected and shown. So when I draft a player, the team roster is update real time. |  | Y |  | Y
61 | Main | Draft Roster | When the program starts it should display players being drafted |  |  | Y
62

## Things to have
Things to have for the installer:
2 png icon files
executable - compiled in release
database file
msvcp100.dll
msvcr100.dll